# Charlton-on-Otmoor C of E Primary School – Climate Action Plan, July 2025 to July 2028

# Items achieved or started are marked in Green and actions to still be completed in Red.

| Action | Benefit |
| --- | --- |
| Discuss arranging an Energy and buildings audit by a specialist. | Identify areas to focus on decarbonising. |
| Replace lighting in buildings with LEDs. | Significant reduction in carbon emissions. |
| Re-establishment of Eco-Crew who are actively working on projects including reducing waste and increasing biodiversity. | Enable children to lead on sustainability and re-accredit Eco-School award. |
| Audited curriculum for sustainable themes. | Understand how sustainability is covered across year groups and raise awareness of areas to expand into. |
| Sustainability training for governors and staff. | Increase awareness of sustainability and carbon literacy. |
| Measure carbon footprint. | Establish baseline to measure emissions against. |
| Apply for Sustainable Primary School award. | Raise profile of sustainability and celebrate success. |
| Conducted pupil voice on sustainability. | Understand how children feel about environmental action. |
| Confirm energy is on a renewable tariff. | Reduce carbon emissions. |
| Established PTA sales of second-hand uniform, at a reduced rate | Reduce clothing waste. |
| Partnership with the School Meal provider to commit to reducing food waste. | Reduce food waste. |
| Ongoing whole-school WOW Walk to School initiative. | Reduce transport emissions, promote active travel and more children walking to school. |
| Introduction of ‘Bug Hotels’ in the Foundation area play ground and Forest school to educate pupils in the importance of insects in our natural environment. | Raise awareness of the importance of insects, bees and birds in our wild life |
| Eco-Crew active in promoting hedgehog highways and holding assemblies about biodiversity. | Increase biodiversity and knowledge about this. |
| Climate Education to be run with Year 6 children. | Support children in climate knowledge and action. |
| Sustainability added to web site - curriculum and CAP. | Inform community about actions and commitment to sustainability. |
| Establish sustainability leadership in school. | Ensure delivery of this plan. |
| Forest School: Educating pupils to understand and look after wildlife and natural areas | To raise awareness of the importance of our natural environment |

| # Overarching sustainability actions |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action | Link to Improvement Plan | Responsibility and Key Stakeholders | Timescale | Information and/or resources required | Target/ Measure | Progress (Update at regular review points) |
| Share/promote CAP with stakeholders | 4.3 Establish sustainability action plan for school | Head; Forest School Lead; | Start Date: 2025-Autumn Review Date: Spring 2025 |  | Ensure children, staff and parents are aware of the plan. |  |
| # Decarbonisation |  |  |  |  |  |  |
| Our Vision: Reduce carbon footprint from the 24-25 calculation |  |  |  |  |  |  |
| Action | Link to Improvement Plan | Responsibility and Key Stakeholders | Timescale | Information and/or resources required | Target/ Measure | Progress (Update at regular review points) |
| LED lighting: review cost impact of replacing LED lights in Main building and hall. |  | SBM | Start date: Autumn 2025 Review Date: Spring 2026 |  | Reduce energy consumption; gather the baseline figure. |  |
| Investigate installation of solar panels and install. |  | SBM | Start date: Autumn 2025 Review Date: Spring 2026 |  | Move energy consumption to on-site renewable sources. |  |
| Run carbon footprint for next year. |  | SBM | Start date: Autumn 2025 Review Date: Autumn 2026 |  |  |  |
| Establish an Eco-Crew and agree focus areas then, take action to reduce emissions. E.g. if energy, investigate Energy Sparks to reduce energy consumption. If food, reduce emissions from food waste. |  | NG/Eco-Crew Lead | Start date: Autumn 2025 Review Date: Spring 2026 | Useful links: Energy Sparks; | Reduce energy consumption and drive sustainable behaviours. |  |
| Continue ‘ Walk to School’ initiative. Work towards Modestars sustainable travel accreditation. |  | NG/Eco-Crew Lead | Start date: Underway Review Date: Spring 2026 | Useful links: Modeshift STARS | Increase active travel to reduce transport emissions |  |
| # Adaptation and Resilience |  |  |  |  |  |  |
| Our Vision Make the estate and people more resilient to climate change |  |  |  |  |  |  |
| Action | Link to Improvement Plan | Responsibility and Key Stakeholders | Timescale | Information and/or resources required | Target/ Measure | Progress (Update at regular review points) |
| Reduce water usage and flood risk by installing a water butt. |  | SBM | Start date: Autumn 2025 Review Date: Spring 2026 | Useful links: Catching every raindrop | Reduced water usage and flood risk |  |
| # Biodiversity |  |  |  |  |  |  |
| Our Vision Make the school grounds more supportive of wildlife. |  |  |  |  |  |  |
| Action | Link to Improvement Plan | Responsibility and Key Stakeholders | Timescale | Information and/or resources required | Target/ Measure | Progress (Update at regular review points) |
| Promote the existence of our Forest School area as a nature area. Build ‘respect for nature’ into every play assembly. |  | Head | Start date: Autumn 2025 Review Date: Summer 2026 | Useful links: |  |  |
| Increase natural habitats in school ground |  | Forest Club | Start date: Summer 2025 Review Date: Spring 2026 | Useful links: |  |  |
| # Climate Education and Green Skills |  |  |  |  |  |  |
| Our Vision (how can you prepare students for a world impacted by climate change through education & practice?): Ensure students and teachers are carbon literate and knowledgeable about their role in creating a sustainable future. |  |  |  |  |  |  |
| Action | Link to Improvement Plan | Responsibility and Key Stakeholders | Timescale | Information and/or resources required | Target/ Measure | Progress (Update at regular review points) |
| Continue to embed sustainability in the curriculum and measure impact |  | Head | Start date: underway Review Date: Autumn 2025 | Useful links: |  |  |
| Plan and deliver teacher CPD to build confidence in climate issues and embed it in curriculum. |  | Head | Start date: Autumn 2025 Review Date: Spring 2026 | Useful links: |  |  |
| Educate/communicate to children on conserving resources, with an emphasis on water, with signage/in play assembly |  | Head | Start date: Review Date: | Useful links: |  |  |